## Sprint 1
Story No | Product Backlog No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
Story1 | PB1 | Login to the system with provided private accounts or with faculty's guest accounts. | Closed | Tung | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4
Story2 | PB2 | Admin manages all users | Closed | Chi | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 5
Story3 | PB3 | Admin assigns a MM to manage the overall process. | Closed | Chi | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 5
Story4 | PB4 | Admin assigns MCs to manage the faculties. | Closed | Hà | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4
Story5 | PB5 | Admin manages faculties | Closed | Hà | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
Story6 | PB11 | Student submits article(s) | Closed | Sơn | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5
Story7 | PB6 | Student needs to agree term to Submit article(s). | Closed | Trường | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 3
|  |  |  | Actual Remaining Hours | 30 | 22 | 15 | 6 | 3 | 2 | 1 | 0
|  |  |  | Estimated Remaining Hours | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0

## Sprint 2
Product Backlog No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
PB7 | Task1 | Student has a list of all submited article(s). | Closed | Tung | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
PB23 | Task2 | Student views his/her submitted article(s) | Closed | Tung | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4
PB9 | Task3 | Student edits submited article(s). | Closed | Chi | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
PB10 | Task4 | Student comments the article(s). | Closed | Sơn | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 4
PB12 | Task5 | Marketing Coordinator receives a notification for each new submited article by student. | Closed | Hà | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 5
PB13 | Task6 | Marketing Coordinator has a list of all submited article(s). | Closed | Sơn | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
PB14 | Task7 | Marketing Coordinator views article(s) content. | Closed | Trường | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
|  |  |  | Actual Remaining Hours | 29 | 24 | 20 | 12 | 9 | 7 | 3 | 0
|  |  |  | Estimated Remaining Hours | 29 | 24.8571 | 20.7143 | 16.5714 | 12.4286 | 8.2857 | 4.1429 | 0

## Sprint 3
Product Backlog No | Task No | Task Description | Status | Owner | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent - Day 6 | Hours Spent - Day 7 | Total Spent Hours
PB15 | Task1 | Marketing Coordinator approves article(s) for the magazine. | Closed | Tung | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
PB16 | Task2 | Marketing Coordinator unapproves article(s). | Closed | Tung | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4
PB20 | Task3 | Marketing Manager receives a notification for each new approved article by MC. | Closed | Chi | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 4
PB18 | Task4 | Marketing Manager has a list of all approved article(s). | Closed | Trường | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 4
PB17 | Task5 | Marketing Manager views approved article(s) | Closed | Hà | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4
PB19 | Task6 | Marketing Manager downloads all approved article(s) in a ZIP file after deadline. | Closed | Hà | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
PB21 | Task7 | Guest views Statistical report(s). | Closed | Sơn | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4
PB22 | Task 8 | Guest views Exceptional report(s). | Closed | Sơn | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
|  |  |  | Actual Remaining Hours | 32 | 27 | 23 | 15 | 12 | 10 | 4 | 0
|  |  |  | Estimated Remaining Hours | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0